## Sheet1
Software Project - Final Project |  |  |  |  | yes
Section | Details | Owner | Due | Done? | no
Configuration | Create a configuration file implamenting SPConfig.h | Shlomi
Testing (creating a unit test)
Preprocessing | Extraction, Non-Extraction mode | Shlomi
Testing (creating a unit test)
SPImage | Already given | Bar* | 2016-09-04 | *Probably no changes are needed
Query | should take 10 minutes to program | Bar | 2016-07-11
Search Similar Images | KD-Array | Bar | 2016-07-11 | yes
Testing (creating a unit test)
| Construction of KD-Tree | Bar | 2016-07-18
Testing (creating a unit test)
| K-Nearest neighbors search | Shlomi
Testing (creating a unit test)
Showing Results | Minimal & Non-Minimal GUI | Bar | 2016-08-01
Testing (creating a unit test)
Testing | Debugging Running on NOVA Checking for memory leaks | Both! | starting on 4/09/2016
SP - Final Project |  | Both! | 2016-09-13